## PARAMETERS
PAR | VALOR
Discount rate | 10% | per annum
Discount rate | 0.02612% | per day
Foundation and reserve timing costs | 500000 | US$ ("sunk cost")
Period costs | 500 | US$/d for a given structure ("fixed costs")
Activity costs |  | Already allocated in "Profit" field function ("marginal costs")

## MACHINES
TYPE | MACHINE | RATE | MACHINE = PARALLEL HEADINGS
0 | 0 | 1 | RATE PER DAY
0 | 1 | 1.3333
0 | 2 | 2
1 | 3 | 200
1 | 4 | 600

## JOBS
ID | DEV TYPE | Driving quantity | PROFIT | Predecessor IDs
913_2e9349b91b40 | PD | 12 | -26700 | 881_740dcee3e8e5
1423_54cf1812623 | PD | 11.8081 | -26273.0475 | 1235_835a036c6b7
1458_fbf8794c9b4 | PD | 10 | -22250 | 1457_520c61aa23e
1458_aa378b9a5fe | PD | 10 | -22250 | 1458_fbf8794c9b4
1458_e11135a3fc9 | PD | 4.4162 | -9826.063 | 1458_aa378b9a5fe
1343_c710ce95383 | PD | 10 | -22250 | 1457_f1c29c8f70f
1343_69dd584ed47 | PD | 10 | -22250 | 1343_c710ce95383
1343_4480e8e7238 | PD | 10 | -22250 | 1343_69dd584ed47
1343_fe5508df5e8 | PD | 5.6114 | -12485.3949 | 1343_4480e8e7238
3457_b218c37fb89 | SD | 10 | -22145.9154 | 3276_ccd5726c4f1
3457_22e02fee5b1 | SD | 10 | 13264.5249 | 3457_b218c37fb89
3457_4fb93259736 | SD | 10 | 14620.9755 | 3457_22e02fee5b1
3457_c9f21112bab | SD | 10 | 13057.756 | 3457_4fb93259736
3457_ffa2fd048e3 | SD | 10 | 13269.9124 | 3457_c9f21112bab
3457_53ecc99170f | SD | 10 | 16126.9126 | 3457_ffa2fd048e3
3457_eb8e4c44725 | SD | 10 | 15168.2177 | 3457_53ecc99170f
3457_60cdf577546 | SD | 10 | 16155.7581 | 3457_eb8e4c44725
3457_44cc4677a4f | SD | 10 | 15609.7642 | 3457_60cdf577546
3457_4cb59e7bcdd | SD | 10 | 15514.576 | 3457_44cc4677a4f
3457_a1b87694cc1 | SD | 10 | 14569.0718 | 3457_4cb59e7bcdd
3457_a6dc842dc94 | SD | 10 | 7768.7309 | 3457_a1b87694cc1
3457_dd4d75789cd | SD | 10 | -24080 | 3457_a6dc842dc94
3457_246c0ff614d | SD | 4.577 | -11021.4778 | 3457_dd4d75789cd
810_9a87061885fc | SD | 10 | 125135.2337 | 882_c555174988b9
810_c7efb85380f6 | SD | 10 | 22924.1959 | 810_9a87061885fc
810_948e76638ac3 | SD | 3.9196 | -9438.5054 | 810_c7efb85380f6
3446_d237d5d89ef | SD | 10 | 3626.0025 | 3380_3254092930c
3446_fc4ad80e1b | SD | 10 | 14133.8852 | 3446_d237d5d89ef
3446_fa91abf38e2 | SD | 10 | 16884.4446 | 3446_fc4ad80e1b
3446_d8395c9c5a8 | SD | 10 | 14342.9949 | 3446_fa91abf38e2
3446_cb7f1c2a65b | SD | 10 | 15214.9566 | 3446_d8395c9c5a8
3446_b5d28d46d79 | SD | 10 | 17242.1554 | 3446_cb7f1c2a65b
3446_38cd2cddff4 | SD | 10 | 16275.3517 | 3446_b5d28d46d79
3446_ccecac3bb0b | SD | 10 | 16998.9068 | 3446_38cd2cddff4
3446_f13c8c0a162 | SD | 10 | 15170.2219 | 3446_ccecac3bb0b
3446_e070967a05e | SD | 10 | 15633.4894 | 3446_f13c8c0a162
3446_f4891677e7 | SD | 10 | 14543.1656 | 3446_e070967a05e
3446_98f21802dc5 | SD | 11.2767 | -27369.3026 | 3446_f4891677e7
1336_cb1f1b5b988 | SD | 10 | 9309.7239 | 1629_90bc9ccb52b
1336_d933ab92433 | SD | 10 | 4314.1809 | 1336_cb1f1b5b988
1336_f46aad8bbd4 | SD | 10 | -28853.2633 | 1336_d933ab92433
1336_e074479c0e1 | SD | 10 | -2590.0734 | 1336_f46aad8bbd4
1336_4b14e1c99ff | SD | 10 | 11130.9055 | 1336_e074479c0e1
1336_ad9ed60d4b0 | SD | 10 | 10864.1766 | 1336_4b14e1c99ff
1336_fcc195f5464 | SD | 10 | -6210.5109 | 1336_ad9ed60d4b0
1336_60139ee7e42 | SD | 10 | 1772.3057 | 1336_fcc195f5464
1336_ce3ff059bd6 | SD | 7.5658 | 1511.7237 | 1336_60139ee7e42
3189_b333da5a792 | SD | 10 | 14049.2765 | 3102_26641eb280a
3189_5bad0580718 | SD | 10 | 14797.3801 | 3189_b333da5a792
3189_ab458010164 | SD | 10 | -24080 | 3189_5bad0580718
3189_12f51e77ac5 | SD | 4.8417 | -11658.8432 | 3189_ab458010164
3258_bca66dffa67 | SD | 11.9549 | 17504.0319 | 3237_89602e10df1
3008_bf6e73ea276 | SD | 10 | 14221.6257 | 2628_13c06ec3778
3008_a477fcf3cd5 | SD | 10 | 15106.5646 | 3008_bf6e73ea276
3008_fc5736888f8 | SD | 10 | 15249.1745 | 3008_a477fcf3cd5
3008_379683f84de | SD | 10 | 19237.584 | 3008_fc5736888f8
3008_fd9e8dad96a | SD | 10 | 10646.0892 | 3008_379683f84de
3008_9bb1000a7a | SD | 10 | 13899.1204 | 3008_fd9e8dad96a
3008_3fde5fa9a8b | SD | 10 | 14806.8595 | 3008_9bb1000a7a
3008_63adbfa14b4 | SD | 10 | 19807.7955 | 3008_3fde5fa9a8b
3008_7beb6a2a557 | SD | 10 | 16133.3156 | 3008_63adbfa14b4
3008_bc4c40fc320 | SD | 10 | 12579.6132 | 3008_7beb6a2a557
3008_7728ab316a3 | SD | 5.8093 | 6070.4597 | 3008_bc4c40fc320
3237_89602e10df1 | SD | 1.8541 | -4464.6281 | 3008_7728ab316a3
2082_77488fc137f | SD | 10 | 11701.0779 | 1629_90bc9ccb52b
2082_dc4c99eb625 | SD | 10 | 12201.8467 | 2082_77488fc137f
2082_430b6974215 | SD | 10 | 11080.7555 | 2082_dc4c99eb625
2082_8390eda8c11 | SD | 10 | 12280.7398 | 2082_430b6974215
2082_5764fb9ad4d | SD | 10 | 12046.1165 | 2082_8390eda8c11
2082_b44523b156d | SD | 10 | 14596.0694 | 2082_5764fb9ad4d
2082_84e84ee8ce6 | SD | 10 | 20982.4078 | 2082_b44523b156d
2082_bdd710bd0ca | SD | 10 | 36264.125 | 2082_84e84ee8ce6
2082_4d61e4cb77a | SD | 10 | 32703.4433 | 2082_bdd710bd0ca
2082_c72367c6cdc | SD | 10 | 27342.6478 | 2082_4d61e4cb77a
2082_cc3e3baa279 | SD | 10 | 22505.7259 | 2082_c72367c6cdc
2082_2001b157d87 | SD | 10 | 27629.0695 | 2082_cc3e3baa279
2082_b203b73adab | SD | 10 | 28537.3785 | 2082_2001b157d87
2082_c2a52aac127 | SD | 10 | -13486.0995 | 2082_b203b73adab
2082_f510aa88d5a | SD | 10 | -30319.0975 | 2082_c2a52aac127
2082_fec88b13c65 | SD | 6.4901 | -15628.2005 | 2082_f510aa88d5a
2506_394fe8274f2 | SD | 1.2353 | -2974.5133 | 2082_fec88b13c65
2708_83c9c884fe9 | SD | 10 | 14768.581 | 2899_842285c0a1f
2708_76221337df | SD | 10 | 20941.5856 | 2708_83c9c884fe9
2708_c12ccd3e6d8 | SD | 10 | 8586.6062 | 2708_76221337df
2708_c308902f24d | SD | 10 | 3223.4121 | 2708_c12ccd3e6d8
2708_6348fee5ccb | SD | 10 | 165.6971 | 2708_c308902f24d
2708_2092edde251 | SD | 10 | -5366.1041 | 2708_6348fee5ccb
2708_c4f68c07908 | SD | 10 | -10350.1953 | 2708_2092edde251
2708_23cf3f7ca89 | SD | 7.3734 | -11585.7559 | 2708_c4f68c07908
2496_f345607fbcd | SD | 1.7273 | -4159.384 | 2708_23cf3f7ca89
1463_c9dedae7c66 | SD | 10 | 131066.2827 | 882_c555174988b9
1463_876c1bd60bf | SD | 10 | 118854.5687 | 1463_c9dedae7c66
1463_f00bc13933a | SD | 10 | 83132.9553 | 1463_876c1bd60bf
1463_c18e6a8f8f8 | SD | 10 | 70086.954 | 1463_f00bc13933a
1463_bd1406becbe | SD | 10 | 24982.7868 | 1463_c18e6a8f8f8
1463_2abb9fb56d1 | SD | 10 | 24185.5553 | 1463_bd1406becbe
1463_a8523375477 | SD | 10 | 30255.4101 | 1463_2abb9fb56d1
1463_2cf1b6b8042 | SD | 10 | 16393.9587 | 1463_a8523375477
1463_ee93dd6b9a6 | SD | 10 | 16277.1213 | 1463_2cf1b6b8042
1463_672c31bf624 | SD | 10 | 13594.5951 | 1463_ee93dd6b9a6
1463_ccf94d34892 | SD | 10 | 27016.7942 | 1463_672c31bf624
1463_a6d324e5f11 | SD | 10 | 25163.9572 | 1463_ccf94d34892
1463_a43ea23fc20 | SD | 10 | 12546.3459 | 1463_a6d324e5f11
1463_4738f651382 | SD | 10 | -1247.0788 | 1463_a43ea23fc20
1463_e64364126c7 | SD | 10 | 414.2492 | 1463_4738f651382
1463_b7c18f8e443 | SD | 10 | -28733.0297 | 1463_e64364126c7
1463_79c7d9e0597 | SD | 10 | -30514.5965 | 1463_b7c18f8e443
1463_56559a1710c | SD | 8.8352 | -21275.1881 | 1463_79c7d9e0597
2257_942c32b203c | SD | 1.3195 | -3177.3266 | 2131_94ea88ee010
2968_eb0f35026c6 | SD | 10 | 14081.5478 | 2899_842285c0a1f
2968_cecc6108858 | SD | 10 | 15227.3335 | 2968_eb0f35026c6
2968_c27497e79b8 | SD | 10 | 11033.2431 | 2968_cecc6108858
2968_756f0d010de | SD | 9.1464 | 3586.5634 | 2968_c27497e79b8
3102_26641eb280a | SD | 6.2279 | -14996.6631 | 2968_756f0d010de
1031_e31ab877099 | SD | 4.1617 | -5594.7602 | 1336_ce3ff059bd6
948_94d50616eee4 | SD | 10 | -24080 | 1031_e31ab877099
948_52382a632fe3 | SD | 11.9177 | -28697.7842 | 948_94d50616eee4
521_327bb87c75d7 | SD | 10 | 479.3756 | 948_52382a632fe3
521_88e3eba2dfac | SD | 10 | 10368.28 | 521_327bb87c75d7
521_7a3dcfb55a69 | SD | 10 | 34138.4574 | 521_88e3eba2dfac
521_ed69d5ddd4d5 | SD | 10 | 84111.3014 | 521_7a3dcfb55a69
521_6166c783b52c | SD | 10 | 35186.023 | 521_ed69d5ddd4d5
521_e3c7cf40b349 | SD | 10 | 19703.8079 | 521_6166c783b52c
521_76d02132f902 | SD | 10 | 22193.921 | 521_e3c7cf40b349
521_55bdb824c8d2 | SD | 10 | 22107.1151 | 521_76d02132f902
521_34507ddee8a8 | SD | 10 | 19474.031 | 521_55bdb824c8d2
521_cec762058a03 | SD | 10 | 30205.7658 | 521_34507ddee8a8
521_d30a0c4ae989 | SD | 10 | 33280.3168 | 521_cec762058a03
521_a7152b87f444 | SD | 10 | 36769.9074 | 521_d30a0c4ae989
521_79ef108038b5 | SD | 6.7464 | 12813.0999 | 521_a7152b87f444
282_868581674530 | SD | 10 | -24080 | 810_948e76638ac3
282_e118dd297778 | SD | 10 | -24080 | 282_868581674530
282_ebc5755abbf7 | SD | 10 | 4468.5558 | 282_e118dd297778
282_f5ec693a7b6d | SD | 10 | 108834.9045 | 282_ebc5755abbf7
282_30d510148715 | SD | 10 | 100127.1849 | 282_f5ec693a7b6d
282_55dcaa1cc317 | SD | 10 | 82964.9025 | 282_30d510148715
282_5775fedf7833 | SD | 10 | 49060.9603 | 282_55dcaa1cc317
282_ddfd6340d8d1 | SD | 10 | 28972.4938 | 282_5775fedf7833
282_70498a84043a | SD | 10 | -876.0005 | 282_ddfd6340d8d1
282_d21a640a51e0 | SD | 10 | -19510.7988 | 282_70498a84043a
282_d294c0400da | SD | 10 | -17055.4961 | 282_d21a640a51e0
282_8d2a710ed1a3 | SD | 10 | -12439.204 | 282_d294c0400da
282_6bd042de50cb | SD | 12.4018 | -6328.3407 | 282_8d2a710ed1a3
195_e2c90cd40a8b | SD | 10 | 6108.0643 | 521_79ef108038b5
195_c525a8c81832 | SD | 4.3942 | -10581.2624 | 195_e2c90cd40a8b
3317_68a582f3254 | SD | 10 | 12187.0086 | 3258_bca66dffa67
3317_afd933edfa0 | SD | 10 | -24080 | 3317_68a582f3254
3317_23d3782848f | SD | 3.4907 | -8405.643 | 3317_afd933edfa0
2131_a2684954213 | SD | 10 | -24080 | 1463_56559a1710c
2131_2b401c3ebd1 | SD | 10 | -24080 | 2131_a2684954213
2131_946d9086e08 | SD | 10 | -24080 | 2131_2b401c3ebd1
2131_a51186859f6 | SD | 10 | -29461.5427 | 2131_946d9086e08
2131_94ea88ee010 | SD | 5.9063 | -14222.4244 | 2131_a51186859f6
1323_d165d342ce2 | PD | 11.9949 | -26688.6267 | 1235_201d9975693
2512_adc0b6625ed | PD | 12 | -26700 | 2513_9d3f88b94c1
1629_90bc9ccb52b | PD | 12 | -27891.6814 | 1617_48f02044d7f
882_c555174988b9 | PD | 12 | 27959.6003 | 881_9a700a8c7513
2899_842285c0a1f | PD | 12 | -29398.768 | 2936_63e97b4d1e6
1235_52a446cda2f | PD | 10 | -22250 | 1457_6c426f722d
1235_3d98552c913 | PD | 10 | -22250 | 1235_52a446cda2f
1235_835a036c6b7 | PD | 10 | -22250 | 1235_3d98552c913
1235_91ffbb7e775 | PD | 10 | -22250 | 1235_835a036c6b7
1235_201d9975693 | PD | 10 | -22250 | 1235_91ffbb7e775
1235_8d02d487fef | PD | 10 | -22250 | 1235_201d9975693
1235_ddd7b8ca992 | PD | 10 | -22250 | 1235_8d02d487fef
1235_bb0f1dddd4c | PD | 10 | -22250 | 1235_ddd7b8ca992
1235_4acf5a1aaa8 | PD | 10 | -22250 | 1235_bb0f1dddd4c
1235_b77a45e394 | PD | 10 | -22250 | 1235_4acf5a1aaa8
1235_527f79e476e | PD | 10 | -22250 | 1235_b77a45e394
1235_e058b4fdda2 | PD | 2.5249 | -5617.8183 | 1235_527f79e476e
1720_3e16a978ef6 | PD | 10 | -22250 | 1457_8b183a8b05b
1720_4968f90d021 | PD | 10 | -22250 | 1720_3e16a978ef6
1720_2780d99295d | PD | 12.3059 | -27380.676 | 1720_4968f90d021
1457_335d0557902 | PD | 10 | -22250 | 1166_53b4ebe5ab
1457_f1c29c8f70f | PD | 10 | -22250 | 1457_335d0557902
1457_7b8fd603176 | PD | 10 | -22250 | 1457_f1c29c8f70f
1457_fec0945b5fa | PD | 10 | -22250 | 1457_7b8fd603176
1457_520c61aa23e | PD | 10 | -22250 | 1457_fec0945b5fa
1457_5166fcae870 | PD | 10 | -22250 | 1457_520c61aa23e
1457_5c28c442518 | PD | 10 | -22250 | 1457_5166fcae870
1457_2d03f3ae618 | PD | 10 | -22250 | 1457_5c28c442518
1457_79b06ef7c13 | PD | 10 | -22250 | 1457_2d03f3ae618
1457_a384aec7938 | PD | 10 | -22250 | 1457_79b06ef7c13
1457_8b183a8b05b | PD | 10 | -22250 | 1457_a384aec7938
1457_184ec01fb75 | PD | 10 | -22250 | 1457_8b183a8b05b;1720_2780d99295d
1457_6c426f722d | PD | 5.549 | -12346.5779 | 1457_184ec01fb75
2133_cdd65942a2c | PD | 10 | -22250 | 1720_2780d99295d
2133_1f289a6d250 | PD | 10 | -22250 | 2133_cdd65942a2c
2133_57b6f9ac66d | PD | 10 | -22250 | 2133_1f289a6d250
2133_871e4120e59 | PD | 10 | -22250 | 2133_57b6f9ac66d
2133_8a15187438f | PD | 10 | -22250 | 2133_871e4120e59
2133_4e2e3fa9360 | PD | 10 | -22250 | 2133_8a15187438f
2133_29e22e68164 | PD | 10 | -22250 | 2133_4e2e3fa9360
2133_e38d7f37f7b | PD | 10 | -22250 | 2133_29e22e68164
2133_8fcca07de0d | PD | 10 | -22250 | 2133_e38d7f37f7b
2133_85002528f2f | PD | 10 | -22250 | 2133_8fcca07de0d
2133_17b73d18bb | PD | 10 | -22250 | 2133_85002528f2f
2133_6c2111ddaea | PD | 10 | -22250 | 2133_17b73d18bb
2133_e0931d64361 | PD | 10 | -22250 | 2133_6c2111ddaea
2133_490c5bf5d60 | PD | 8.7279 | -19419.6464 | 2133_e0931d64361
2794_46f030653dc | PD | 10 | -22250
2794_68be01b3333 | PD | 10 | -22250 | 2794_46f030653dc
2794_10004634026 | PD | 10 | -22250 | 2794_68be01b3333
2794_ad49825a836 | PD | 10 | -22250 | 2794_10004634026
2794_a7dc2e00f74 | PD | 10 | -22250 | 2794_ad49825a836
2794_8d07db3902f | PD | 10 | -22250 | 2794_a7dc2e00f74
2794_7e499fc400b | PD | 10 | -22250 | 2794_8d07db3902f
2794_40484c21b4c | PD | 10 | -22250 | 2794_7e499fc400b
2794_d457fa43167 | PD | 10 | -22250 | 2794_40484c21b4c
2794_f1482e0c6cb | PD | 7.1808 | -15977.3584 | 2794_d457fa43167
1166_53b4ebe5ab | PD | 11.9887 | -26674.9384
2628_ff52525348e | PD | 10 | -22250 | 2513_9d3f88b94c1
2628_3b20de13e95 | PD | 10 | -22250 | 2628_ff52525348e
2628_6f76adcd4a1 | PD | 10 | -22250 | 2628_3b20de13e95
2628_4f72a6d9893 | PD | 10 | -22250 | 2628_6f76adcd4a1
2628_13c06ec3778 | PD | 5.0711 | 1288.9526 | 2628_4f72a6d9893
3380_5130cc4756d | PD | 10 | -22250 | 3317_23d3782848f
3380_3254092930c | PD | 10.7133 | -23837.1068 | 3380_5130cc4756d
3276_ccd5726c4f1 | PD | 11.4459 | -25467.2173 | 3189_12f51e77ac5
881_24aad59fb6e6 | PD | 10 | -22250 | 1235_e058b4fdda2
881_740dcee3e8e5 | PD | 10 | -22250 | 881_24aad59fb6e6
881_a19c03d89a12 | PD | 10 | -22250 | 881_740dcee3e8e5
881_6da6a43287e3 | PD | 10 | -22250 | 881_a19c03d89a12
881_7b815cdab0cc | PD | 10 | -22250 | 881_6da6a43287e3
881_9a700a8c7513 | PD | 4.0092 | 25627.5749 | 881_7b815cdab0cc
1617_dbba5f8484 | PD | 10 | -22250 | 1457_6c426f722d
1617_1367642ccb | PD | 10 | -22250 | 1617_dbba5f8484
1617_5dc5f8e1caa | PD | 10 | -22250 | 1617_1367642ccb
1617_48f02044d7f | PD | 9.4408 | -21005.8231 | 1617_5dc5f8e1caa
2513_b2230cb917f | PD | 10 | -22250 | 2133_490c5bf5d60
2513_af54ced9b7f | PD | 10 | -22250 | 2513_b2230cb917f
2513_b7f323791cb | PD | 10 | -22250 | 2513_af54ced9b7f
2513_98a3d46ef7f | PD | 10 | -22250 | 2513_b7f323791cb
2513_ced9c78e7a3 | PD | 10 | -22250 | 2513_98a3d46ef7f
2513_9d3f88b94c1 | PD | 11.596 | -25800.9997 | 2513_ced9c78e7a3
2936_b94bac445e5 | PD | 10 | -22250 | 2794_d457fa43167
2936_34a4303ab02 | PD | 10 | -22250 | 2936_b94bac445e5
2936_89f5fcd7489 | PD | 10 | -22250 | 2936_34a4303ab02
2936_f7d440841b5 | PD | 10 | -22250 | 2936_89f5fcd7489
2936_63e97b4d1e6 | PD | 8.8477 | -24809.161 | 2936_f7d440841b5
2540_4133e78099d | NA | 226.0597 | -1009.042 | 2496_f345607fbcd
2560_1cbdf873d85 | NA | 241.8301 | 10874.9949 | 2708_c4f68c07908;2540_4133e78099d
2594_e540b53166f | NA | 407.9146 | 22491.0402 | 2708_c4f68c07908;2560_1cbdf873d85
2620_7cb377ba174 | NA | 604.2142 | 30607.0954 | 2708_2092edde251;2594_e540b53166f
2648_8bf9875da59 | NA | 596.2322 | 44575.4833 | 2708_2092edde251;2620_7cb377ba174
2672_945bf903d79 | NA | 624.0556 | 48103.5136 | 2708_6348fee5ccb;2648_8bf9875da59
2700_ddfa73ef13 | NA | 648.0609 | 51067.7137 | 2708_6348fee5ccb;2672_945bf903d79
2727_c24578381ec | NA | 639.5498 | 52391.9313 | 2708_c308902f24d;2700_ddfa73ef13
2749_242e858d35 | NA | 689.8978 | 56042.7181 | 2708_c308902f24d;2727_c24578381ec
2769_f55234dc940 | NA | 448.9459 | 38834.3162 | 3008_bf6e73ea276;2806_2b0478088e5
2775_86d0122e429 | NA | 756.9267 | 60928.2461 | 2708_c12ccd3e6d8;2749_242e858d35
2806_2b0478088e5 | NA | 968.1176 | 49486.2746 | 3008_a477fcf3cd5;2834_544750f5ca2
2803_66d4dddd56e | NA | 788.5526 | 65216.5253 | 2708_c12ccd3e6d8;2775_86d0122e429
2834_544750f5ca2 | NA | 1128.7087 | 91207.2844 | 3008_a477fcf3cd5;2858_9c1dff86570
2829_7219ff33ac0 | NA | 944.0352 | 69314.8895 | 2708_76221337df;2803_66d4dddd56e
2858_9c1dff86570 | NA | 1480.3956 | 121974.1374 | 3008_a477fcf3cd5;2881_9706dcaf14b
2855_601069cb11 | NA | 1063.0284 | 84953.9336 | 2708_76221337df;2829_7219ff33ac0
2881_9706dcaf14b | NA | 1566.4999 | 122421.829 | 3008_fc5736888f8;2907_11560b59e2e
2879_a5295629d7 | NA | 1152.127 | 91886.4211 | 2708_83c9c884fe9;2855_601069cb11
2907_11560b59e2e | NA | 1573.3111 | 127081.6806 | 3008_fc5736888f8;2931_4325493d38e
2906_bb55e686332 | NA | 1074.6015 | 80081.4065 | 2708_83c9c884fe9;2879_a5295629d7;2954_f2c4b0bd29e
2931_4325493d38e | NA | 1551.459 | 140274.5577 | 3008_379683f84de;2957_58b4f44898b
2957_58b4f44898b | NA | 1501.4387 | 136730.2548 | 3008_379683f84de;2982_e8952e0c225
2954_f2c4b0bd29e | NA | 1199.8751 | 91875.1255 | 2968_eb0f35026c6;2978_ca2ca3d471b
2982_e8952e0c225 | NA | 1456.9489 | 123975.7901 | 3008_fd9e8dad96a;3005_70cd9decb12
2978_ca2ca3d471b | NA | 1221.5357 | 97459.9576 | 2968_cecc6108858;3003_aade302c9fd
3005_70cd9decb12 | NA | 1209.1162 | 93447.2512 | 3008_fd9e8dad96a;3029_28721c7c907
3003_aade302c9fd | NA | 1205.9888 | 97125.9445 | 2968_cecc6108858;3028_3e34651efbd
3029_28721c7c907 | NA | 1177.7421 | 89005.5062 | 3008_9bb1000a7a;3051_e23c5eee491
3028_3e34651efbd | NA | 1333.6254 | 103384.1898 | 2968_c27497e79b8;3049_3b04f985dd
3051_e23c5eee491 | NA | 1174.1262 | 84148.5428 | 3008_9bb1000a7a;3074_bda44892645
3049_3b04f985dd | NA | 1200.5119 | 100206.2903 | 2968_c27497e79b8;3076_e907ad09309
3074_bda44892645 | NA | 1119.9817 | 89160.2283 | 3008_3fde5fa9a8b;3097_bd3e327d827
3076_e907ad09309 | NA | 1104.8813 | 79868.4637 | 2968_756f0d010de;3092_e246696357e
3097_bd3e327d827 | NA | 1204.5151 | 87683.4239 | 3008_3fde5fa9a8b;3117_fda925bd8a2
3092_e246696357e | NA | 976.2561 | 67166.8952 | 2968_756f0d010de;3119_295b3671e45
3117_fda925bd8a2 | NA | 1179.954 | 90413.9619 | 3008_63adbfa14b4;3139_7c72dfd8007
3119_295b3671e45 | NA | 948.4014 | 41292.7557 | 3102_26641eb280a;3140_ea2c5b33184
3139_7c72dfd8007 | NA | 1164.1392 | 100453.18 | 3008_63adbfa14b4;3159_2c78b295960
3140_ea2c5b33184 | NA | 891.8479 | 12258.083 | 3189_b333da5a792;3170_4a5993e46f0
3159_2c78b295960 | NA | 1171.348 | 92000.6983 | 3008_7beb6a2a557;3181_c838d283715
3181_c838d283715 | NA | 1171.6208 | 84490.4523 | 3008_7beb6a2a557;3199_8ad421d6107
3199_8ad421d6107 | NA | 1118.5559 | 82325.0899 | 3008_bc4c40fc320;3216_112926f52f
3216_112926f52f | NA | 918.0383 | 75223.0868 | 3008_bc4c40fc320;3235_3e8debb828f
3235_3e8debb828f | NA | 841.3624 | 61212.3459 | 3008_7728ab316a3;3253_f100fd16e27
3253_f100fd16e27 | NA | 806.5359 | 32706.2968 | 3258_bca66dffa67;3237_89602e10df1;3269_5e2e110d68e
3269_5e2e110d68e | NA | 751.6107 | 5453.3564 | 3258_bca66dffa67;3299_487e90c4d4a
151_4b3893ac16db | NA | 33.4714 | 3970.8961 | 282_6bd042de50cb
161_92613191683a | NA | 338.1125 | 24421.6948 | 282_6bd042de50cb;151_4b3893ac16db
171_7c72a0a433bc | NA | 536.3912 | 41498.2615 | 282_8d2a710ed1a3;161_92613191683a
183_959aa7d77b85 | NA | 565.3007 | 53225.1902 | 282_8d2a710ed1a3;171_7c72a0a433bc
198_5df320369c66 | NA | 562.5196 | 53025.0739 | 282_d294c0400da;183_959aa7d77b85
214_4bed07598636 | NA | 500.4649 | 34006.5301 | 282_d294c0400da;198_5df320369c66
208_7ced1235382b | NA | 331.9274 | 19197.2193 | 195_c525a8c81832;195_e2c90cd40a8b
231_399626def4 | NA | 501.201 | 35147.945 | 282_d21a640a51e0;214_4bed07598636
223_4506b3bcda1b | NA | 558.9022 | 47258.1257 | 521_79ef108038b5;208_7ced1235382b
253_f7b8a7974811 | NA | 484.4449 | 34922.9363 | 282_d21a640a51e0;231_399626def4
239_db5ee4ee3d72 | NA | 529.9637 | 55496.7687 | 521_79ef108038b5;223_4506b3bcda1b
272_43c210f24cd2 | NA | 558.3501 | 48047.9243 | 282_70498a84043a;253_f7b8a7974811
262_78cf36f68d01 | NA | 559.3972 | 64812.9023 | 521_a7152b87f444;239_db5ee4ee3d72
295_88df4595ba6b | NA | 565.4915 | 47902.178 | 282_70498a84043a;272_43c210f24cd2
280_e612c4981a51 | NA | 563.6672 | 69264.809 | 521_a7152b87f444;262_78cf36f68d01
317_723f6ecbd0ac | NA | 562.4267 | 40875.4635 | 282_ddfd6340d8d1;295_88df4595ba6b
304_a9361b5cf41f | NA | 561.3491 | 74852.4673 | 521_d30a0c4ae989;280_e612c4981a51
342_f0c4a9414e4 | NA | 547.0516 | 40029.9481 | 282_ddfd6340d8d1;317_723f6ecbd0ac
328_67f8a21b773f | NA | 569.755 | 82607.8466 | 521_cec762058a03;304_a9361b5cf41f
367_a33e77730834 | NA | 560.7513 | 42225.0534 | 282_5775fedf7833;342_f0c4a9414e4
353_76138f46cc67 | NA | 569.7111 | 103147.4164 | 521_cec762058a03;328_67f8a21b773f
396_a8af757e0f6a | NA | 579.6635 | 56640.0397 | 282_5775fedf7833;367_a33e77730834
380_cb099b985f75 | NA | 560.7657 | 119695.9063 | 521_34507ddee8a8;353_76138f46cc67
420_20031bff08f1 | NA | 570.9736 | 68000.6782 | 282_55dcaa1cc317;396_a8af757e0f6a
408_6489ee0884b7 | NA | 556.1584 | 75284.9126 | 521_34507ddee8a8;380_cb099b985f75
445_e15ad0ded36b | NA | 557.6219 | 66899.7658 | 282_55dcaa1cc317;420_20031bff08f1
434_b4ce950f66 | NA | 563.8844 | 80174.751 | 521_55bdb824c8d2;408_6489ee0884b7
470_7e377bf44ad6 | NA | 561.0621 | 88377.8223 | 282_30d510148715;445_e15ad0ded36b
459_9525942cac6 | NA | 564.0192 | 77513.0804 | 521_55bdb824c8d2;434_b4ce950f66
498_e3d2c9bad423 | NA | 559.279 | 82140.8356 | 282_30d510148715;470_7e377bf44ad6
482_81bb3766e01e | NA | 562.4464 | 81153.4041 | 521_76d02132f902;459_9525942cac6
511_6cb0a90486e2 | NA | 555.6512 | 74419.4044 | 521_76d02132f902;482_81bb3766e01e
551_a18734352c76 | NA | 563.7866 | 231721.8229 | 282_f5ec693a7b6d;498_e3d2c9bad423
535_79c986075f73 | NA | 567.5835 | 71847.3012 | 521_e3c7cf40b349;511_6cb0a90486e2
579_e5f17c260bd2 | NA | 570.4062 | 240556.8585 | 282_ebc5755abbf7;551_a18734352c76
604_209bec0d1edf | NA | 563.7498 | 200250.2386 | 282_ebc5755abbf7;579_e5f17c260bd2
587_d7069d8d2f5e | NA | 578.8883 | 73176.2762 | 521_6166c783b52c;535_79c986075f73
634_2bd6d0896f5d | NA | 574.3887 | 106928.7179 | 282_e118dd297778;604_209bec0d1edf
614_9858b1675b29 | NA | 543.1971 | 74341.0435 | 521_6166c783b52c;587_d7069d8d2f5e
663_f644791facd3 | NA | 508.2827 | 37088.3765 | 282_e118dd297778;634_2bd6d0896f5d
641_224dac7e35d1 | NA | 565.8987 | 92084.6457 | 521_ed69d5ddd4d5;614_9858b1675b29
693_6d43f9688c10 | NA | 507.0546 | 36586.5945 | 282_868581674530;663_f644791facd3
674_44623cfea240 | NA | 579.8565 | 100212.4155 | 521_ed69d5ddd4d5;641_224dac7e35d1
720_e2e483a8c258 | NA | 503.7019 | 23188.1784 | 282_868581674530;693_6d43f9688c10
699_1a8033923874 | NA | 584.1383 | 132871.9743 | 521_7a3dcfb55a69;674_44623cfea240
752_cf728f5721bc | NA | 527.635 | -214.1618 | 810_948e76638ac3;720_e2e483a8c258
729_9fd102a338a4 | NA | 573.852 | 115071.0754 | 521_7a3dcfb55a69;699_1a8033923874
780_ccc3de98e305 | NA | 0 | 0 | 810_c7efb85380f6;752_cf728f5721bc
757_57d13cb5266a | NA | 565.802 | 114196.6189 | 521_7a3dcfb55a69;729_9fd102a338a4
811_fce9677ff830 | NA | 0 | 0 | 810_c7efb85380f6;780_ccc3de98e305
786_8af147281323 | NA | 592.6009 | 88062.533 | 521_88e3eba2dfac;757_57d13cb5266a
844_a3a307025626 | NA | 590.7776 | 28546.7914 | 810_9a87061885fc;811_fce9677ff830;904_c2cd9dde174f
818_4ac04703ce19 | NA | 596.6578 | 66625.5963 | 521_88e3eba2dfac;786_8af147281323
848_9412f55ab806 | NA | 587.8174 | 77478.0099 | 521_327bb87c75d7;818_4ac04703ce19
904_c2cd9dde174f | NA | 954.4694 | 155287.6396 | 1463_c9dedae7c66;932_3addf9217e56
878_e4fe5bd75cf | NA | 578.5139 | 89155.4758 | 521_327bb87c75d7;848_9412f55ab806
932_3addf9217e56 | NA | 1083.2198 | 227043.3136 | 1463_c9dedae7c66;962_a8622c9f484f
911_a797ea1ca5ec | NA | 562.7504 | 75265.0665 | 948_52382a632fe3;878_e4fe5bd75cf
962_a8622c9f484f | NA | 1184.6127 | 229812.6875 | 1463_876c1bd60bf;998_f9981dc3a90a
937_b97421afc55b | NA | 569.3903 | 54126.7266 | 948_52382a632fe3;911_a797ea1ca5ec
998_f9981dc3a90a | NA | 1219.8979 | 183947.14 | 1463_876c1bd60bf;1027_712f964a717
968_323b85038a63 | NA | 386.7412 | 7429.8717 | 948_94d50616eee4;937_b97421afc55b
1027_712f964a717 | NA | 1225.2007 | 149263.7021 | 1463_f00bc13933a;1062_12de4188f6d
1062_12de4188f6d | NA | 1226.5355 | 115555.5613 | 1463_f00bc13933a;1097_74632b849d3
1050_b944265b1f6 | NA | 86.7849 | 2146.8026 | 1336_ce3ff059bd6;968_323b85038a63
1097_74632b849d3 | NA | 1172.6647 | 90116.3331 | 1463_c18e6a8f8f8;1133_978a7a8d906
1078_e5b462db2b6 | NA | 800.6234 | -7549.1987 | 1336_ce3ff059bd6;968_323b85038a63
1133_978a7a8d906 | NA | 1013.1752 | 84028.4989 | 1463_c18e6a8f8f8;1167_5f2108d90f4
1112_a02bab3c1ba | NA | 960.743 | 6537.1536 | 1336_60139ee7e42;1050_b944265b1f6;1078_e5b462db2b6
1167_5f2108d90f4 | NA | 1156.2048 | 84120.6656 | 1463_bd1406becbe;1199_1be4b5ee146
1144_19eb5857b18 | NA | 1113.3114 | 17230.0078 | 1336_60139ee7e42;1112_a02bab3c1ba
1199_1be4b5ee146 | NA | 1062.7574 | 88019.0162 | 1463_bd1406becbe;1231_b8664d245c3
1180_d0e3924a1b0 | NA | 1233.1328 | 32480.9058 | 1336_fcc195f5464;1144_19eb5857b18
1231_b8664d245c3 | NA | 1258.5684 | 100913.3453 | 1463_2abb9fb56d1;1263_933827d49b
1215_cac47f7352e | NA | 1390.3167 | 41893.901 | 1336_fcc195f5464;1180_d0e3924a1b0
1263_933827d49b | NA | 1128.2867 | 89537.396 | 1463_2abb9fb56d1;1298_62af87a1744
1246_bc4cf99b460 | NA | 1472.9934 | 49512.8036 | 1336_ad9ed60d4b0;1215_cac47f7352e
1298_62af87a1744 | NA | 1304.4388 | 97788.8521 | 1463_a8523375477;1334_4efa430dff3
1275_63b71431218 | NA | 1380.4917 | 53028.6527 | 1336_ad9ed60d4b0;1246_bc4cf99b460
1334_4efa430dff3 | NA | 1308.3825 | 99369.5273 | 1463_a8523375477;1363_541dc7638b6
1308_34bcdcc4892 | NA | 1200.6871 | 54880.6507 | 1336_4b14e1c99ff;1275_63b71431218
1363_541dc7638b6 | NA | 1103.6319 | 91580.0024 | 1463_2cf1b6b8042;1396_257e83d313a
1347_959c1912ea0 | NA | 1074.6175 | 59820.8237 | 1336_4b14e1c99ff;1308_34bcdcc4892
1396_257e83d313a | NA | 1043.3197 | 79408.3737 | 1463_ee93dd6b9a6;1428_8d684627cb
1375_570d4dc6833 | NA | 941.765 | 54006.3625 | 1336_e074479c0e1;1347_959c1912ea0
1428_8d684627cb | NA | 1009.1717 | 73987.6924 | 1463_ee93dd6b9a6;1498_90852efdef9
1410_5d5c8237c72 | NA | 832.9037 | 46331.2214 | 1336_e074479c0e1;1375_570d4dc6833
1441_9e9e0e4de9c | NA | 755.5055 | 41407.5568 | 1336_f46aad8bbd4;1410_5d5c8237c72
1498_90852efdef9 | NA | 985.1479 | 69238.6772 | 1463_672c31bf624;1528_75d84dcf472
1476_ba0e411d4f1 | NA | 663.631 | 25865.5338 | 1336_d933ab92433;1441_9e9e0e4de9c
1528_75d84dcf472 | NA | 993.1785 | 67173.3885 | 1463_ccf94d34892;1559_f17b1830767
1516_b1cbbaf7de2 | NA | 61.4813 | 3519.5099 | 1336_d933ab92433;1476_ba0e411d4f1
1559_f17b1830767 | NA | 972.6088 | 70657.1187 | 1463_ccf94d34892;1596_55d7d392406
1596_55d7d392406 | NA | 1075.5803 | 81393.4737 | 1463_a6d324e5f11;1631_4704833438b
1580_b497cc592b | NA | 280.7584 | 12680.3903 | 1336_cb1f1b5b988;1516_b1cbbaf7de2
1631_4704833438b | NA | 1098.3326 | 81993.9606 | 1463_a6d324e5f11;1661_3926e3e891a
1615_b75fd053999 | NA | 222.3694 | 15413.7334 | 1336_cb1f1b5b988;1580_b497cc592b;1645_ea2080cb74f
1661_3926e3e891a | NA | 1003.0052 | 79547.1521 | 1463_a6d324e5f11;1694_6eefa6f2cf2
1645_ea2080cb74f | NA | 650.5274 | 13229.4168 | 2082_77488fc137f;1677_6e67b624618
1694_6eefa6f2cf2 | NA | 1018.6583 | 79868.0712 | 1463_a43ea23fc20;1726_2c61bf92a9b
1677_6e67b624618 | NA | 649.0128 | 26439.6458 | 2082_dc4c99eb625;1706_9a2eeab2cb9
1726_2c61bf92a9b | NA | 1040.4836 | 74094.4763 | 1463_a43ea23fc20;1753_9c46a10c142
1706_9a2eeab2cb9 | NA | 640.118 | 33342.2739 | 2082_dc4c99eb625;1739_30249e3acef
1753_9c46a10c142 | NA | 1021.9172 | 65918.5372 | 1463_4738f651382;1787_102f6b334f2
1739_30249e3acef | NA | 654.2884 | 38018.9362 | 2082_430b6974215;1772_8d014eb4ff
1787_102f6b334f2 | NA | 965.4222 | 73712.2917 | 1463_4738f651382;1811_3405b42383c
1772_8d014eb4ff | NA | 700.1066 | 38254.2144 | 2082_430b6974215;1802_30267ab3f28
1811_3405b42383c | NA | 870.9115 | 66735.6497 | 1463_e64364126c7;1846_991c2cdbe6e
1802_30267ab3f28 | NA | 825.8951 | 36390.6493 | 2082_8390eda8c11;1830_a07681df733
1846_991c2cdbe6e | NA | 779.028 | 50094.3166 | 1463_e64364126c7;1879_bc08808d329
1830_a07681df733 | NA | 996.7219 | 36166.0531 | 2082_8390eda8c11;1860_49c7e307caa
1879_bc08808d329 | NA | 746.4014 | 41568.7199 | 1463_b7c18f8e443;1906_c26775b8abd
1860_49c7e307caa | NA | 1163.9327 | 35066.5595 | 2082_8390eda8c11;1886_abc37bd69c
1906_c26775b8abd | NA | 648.0758 | 30556.8787 | 1463_b7c18f8e443;1939_7c5f4f7dd8
1886_abc37bd69c | NA | 1220.4185 | 29788.8491 | 2082_5764fb9ad4d;1915_9b082ae5f64
1939_7c5f4f7dd8 | NA | 688.2481 | 10743.2547 | 1463_79c7d9e0597;1966_7d0cc493019
1915_9b082ae5f64 | NA | 1123.077 | 42330.2798 | 2082_5764fb9ad4d;1944_a28bd60dc01
1966_7d0cc493019 | NA | 733.5069 | -8411.281 | 1463_56559a1710c;1463_79c7d9e0597;2052_3421b9c3fcb
1944_a28bd60dc01 | NA | 1022.9774 | 64256.0905 | 2082_b44523b156d;1969_ec0dbfdd593
1969_ec0dbfdd593 | NA | 1118.0057 | 81778.164 | 2082_b44523b156d;1997_802f574c702
1997_802f574c702 | NA | 997.8074 | 79137.652 | 2082_84e84ee8ce6;2033_4d53b496260
2052_3421b9c3fcb | NA | 628.2272 | -7856.2427 | 2131_2b401c3ebd1;2074_4ed7152bd31
2033_4d53b496260 | NA | 1005.8552 | 83709.883 | 2082_84e84ee8ce6;2079_ed3265a9cbf
2074_4ed7152bd31 | NA | 595.7539 | -5814.5084 | 2131_2b401c3ebd1;2099_74b681ecb78
2099_74b681ecb78 | NA | 372.1194 | -1140.5566 | 2131_2b401c3ebd1;2121_658033253f3
2079_ed3265a9cbf | NA | 1098.5215 | 108361.5526 | 2082_bdd710bd0ca;2102_d97f9bdc201
2121_658033253f3 | NA | 658.0903 | -683.6288 | 2131_946d9086e08;2146_9fbffe2c939
2102_d97f9bdc201 | NA | 1055.3013 | 102042.6268 | 2082_4d61e4cb77a;2129_e4bd51800b7
2146_9fbffe2c939 | NA | 622.7967 | -456.4961 | 2131_946d9086e08;2170_f06f2981e95
2129_e4bd51800b7 | NA | 1051.5386 | 115049.5736 | 2082_4d61e4cb77a;2154_633e23c46f9
2170_f06f2981e95 | NA | 568.7105 | -388.8442 | 2131_a51186859f6;2200_99b6acc169d
2154_633e23c46f9 | NA | 974.7996 | 111184.4288 | 2082_c72367c6cdc;2179_c8972a0c3b7
2200_99b6acc169d | NA | 359.3885 | -1662.5801 | 2257_942c32b203c;2131_94ea88ee010;2131_a51186859f6;2230_29618d3c700
2179_c8972a0c3b7 | NA | 925.03 | 103645.5781 | 2082_c72367c6cdc;2207_28501f5977
2230_29618d3c700 | NA | 531.6909 | -4209.6482 | 2131_94ea88ee010
2207_28501f5977 | NA | 895.2923 | 103496.9835 | 2082_cc3e3baa279;2236_91962d3ebee
2236_91962d3ebee | NA | 841.6841 | 100713.4431 | 2082_cc3e3baa279;2263_3d19dfa6619
2263_3d19dfa6619 | NA | 839.1895 | 102221.3756 | 2082_2001b157d87;2288_541db05903f
2288_541db05903f | NA | 818.407 | 112724.6616 | 2082_2001b157d87;2315_4daa24cb7e2
2315_4daa24cb7e2 | NA | 810.9748 | 103919.9255 | 2082_b203b73adab;2346_c2399576c12
2346_c2399576c12 | NA | 796.5106 | 98495.5475 | 2082_b203b73adab;2378_d8913c7a9c1
2378_d8913c7a9c1 | NA | 802.843 | 102347.493 | 2082_c2a52aac127;2404_5c9c47c6cca
2404_5c9c47c6cca | NA | 786.3513 | 87155.7483 | 2082_c2a52aac127;2429_4e64e50489c
2429_4e64e50489c | NA | 670.2487 | 55206.4757 | 2082_f510aa88d5a;2458_6d30e8eeb10
2458_6d30e8eeb10 | NA | 541.7102 | 20508.743 | 2082_f510aa88d5a;2491_2dd3beda174
2491_2dd3beda174 | NA | 482.359 | -1226.5076 | 2506_394fe8274f2
3170_4a5993e46f0 | NA | 700.8266 | 72229.0882 | 3189_5bad0580718;3186_5e37f9fc0c0
3186_5e37f9fc0c0 | NA | 695.158 | 82183.4378 | 3189_5bad0580718;3205_76880d6711f
3205_76880d6711f | NA | 696.597 | 77981.1456 | 3189_5bad0580718;3226_b75ccfbd380
3226_b75ccfbd380 | NA | 678.486 | 61689.0265 | 3189_ab458010164;3244_5dcc58139ee
3244_5dcc58139ee | NA | 594.8992 | 20189.114 | 3189_12f51e77ac5;3189_ab458010164;3306_f9d649fb09b
3299_487e90c4d4a | NA | 696.6903 | 78283.4271 | 3317_68a582f3254;3311_aedf46a7d15
3311_aedf46a7d15 | NA | 693.7232 | 78367.5784 | 3317_afd933edfa0;3328_34f0108e995
3306_f9d649fb09b | NA | 47.7376 | -139.4211 | 3457_b218c37fb89;3321_d8b191ce8e3
3328_34f0108e995 | NA | 689.5435 | 55056.8386 | 3317_afd933edfa0;3344_e2377789aba
3321_d8b191ce8e3 | NA | 56.2918 | 4985.1188 | 3457_22e02fee5b1;3339_391964d523e
3344_e2377789aba | NA | 565.72 | 17870.2334 | 3317_23d3782848f;3415_4431de7a0ef
3339_391964d523e | NA | 257.8358 | 26955.9219 | 3457_22e02fee5b1;3355_4a384a2be28
3355_4a384a2be28 | NA | 466.9867 | 51070.9628 | 3457_22e02fee5b1;3369_ed218a86501
3369_ed218a86501 | NA | 695.8494 | 73618.1535 | 3457_4fb93259736;3381_7a667e8bf8b
3381_7a667e8bf8b | NA | 695.8148 | 80039.7553 | 3457_4fb93259736;3394_5b656d20d52
3394_5b656d20d52 | NA | 684.1577 | 80090.2779 | 3457_c9f21112bab;3404_d4540a87ca9
3404_d4540a87ca9 | NA | 694.1211 | 80320.8832 | 3457_c9f21112bab;3416_f98857286ec
3415_4431de7a0ef | NA | 57.0195 | 6010.5688 | 3446_d237d5d89ef;3425_123d7789e28
3416_f98857286ec | NA | 697.057 | 81133.0756 | 3457_ffa2fd048e3;3426_41aca9bde52
3425_123d7789e28 | NA | 261.6236 | 27396.5171 | 3446_fc4ad80e1b;3438_6870021634a
3426_41aca9bde52 | NA | 716.1873 | 81320.9146 | 3457_ffa2fd048e3;3437_ab1025f5502
3438_6870021634a | NA | 462.9232 | 50538.7086 | 3446_fc4ad80e1b;3449_89648bf9a57
3437_ab1025f5502 | NA | 698.5792 | 81744.3063 | 3457_53ecc99170f;3448_68f7a2111ff
3449_89648bf9a57 | NA | 678.5817 | 73905.7952 | 3446_fc4ad80e1b;3458_d3a0c29d80f
3448_68f7a2111ff | NA | 682.965 | 83337.62 | 3457_53ecc99170f;3456_81bc7cd65b6
3458_d3a0c29d80f | NA | 679.1981 | 86295.0336 | 3446_fa91abf38e2;3466_e0266571585
3456_81bc7cd65b6 | NA | 675.0656 | 82930.7934 | 3457_eb8e4c44725;3465_5de61541631
3466_e0266571585 | NA | 676.6471 | 87403.946 | 3446_fa91abf38e2;3473_e8fe8e39c02
3465_5de61541631 | NA | 698.3528 | 84502.196 | 3457_eb8e4c44725;3480_85e93ef87c6
3473_e8fe8e39c02 | NA | 688.6748 | 87087.0901 | 3446_d8395c9c5a8;3481_117b7c24f3
3481_117b7c24f3 | NA | 722.5708 | 88004.766 | 3446_d8395c9c5a8;3487_31dd302aea
3480_85e93ef87c6 | NA | 690.8284 | 84653.8926 | 3457_60cdf577546;3486_3ab401d11e
3487_31dd302aea | NA | 710.6337 | 86667.6004 | 3446_cb7f1c2a65b;3493_704762eab2
3486_3ab401d11e | NA | 736.1691 | 86586.6103 | 3457_44cc4677a4f;3492_3a79c04cc72
3493_704762eab2 | NA | 695.2583 | 83526.7301 | 3446_cb7f1c2a65b;3500_9c5a29d0449
3492_3a79c04cc72 | NA | 758.3815 | 84563.0089 | 3457_44cc4677a4f;3498_b8cca3a49ae
3500_9c5a29d0449 | NA | 710.8735 | 84087.7745 | 3446_b5d28d46d79;3506_2acf4815c1a
3498_b8cca3a49ae | NA | 735.5764 | 84969.846 | 3457_4cb59e7bcdd;3504_75f2222bd8b
3506_2acf4815c1a | NA | 701.8026 | 87864.3832 | 3446_b5d28d46d79;3512_8c04def5847
3504_75f2222bd8b | NA | 696.1256 | 84475.6838 | 3457_4cb59e7bcdd;3511_ce1e366616a
3512_8c04def5847 | NA | 708.2225 | 88821.5858 | 3446_38cd2cddff4;3517_12e55b4927b
3511_ce1e366616a | NA | 690.1549 | 85633.0911 | 3457_a1b87694cc1;3516_8e81ee3a63e
3517_12e55b4927b | NA | 698.7724 | 87287.4864 | 3446_38cd2cddff4;3521_e13ce5fb726
3516_8e81ee3a63e | NA | 724.1699 | 84454.045 | 3457_a1b87694cc1;3520_5d9dfde30db
3521_e13ce5fb726 | NA | 696.9852 | 86871.7547 | 3446_ccecac3bb0b;3525_b9978dbe434
3520_5d9dfde30db | NA | 747.4657 | 81293.3274 | 3457_a6dc842dc94;3524_530bfe406bb
3525_b9978dbe434 | NA | 683.6719 | 86606.4775 | 3446_ccecac3bb0b;3529_e5b7077154
3524_530bfe406bb | NA | 727.8023 | 76151.6186 | 3457_a6dc842dc94;3528_8b65e7c0cfa
3529_e5b7077154 | NA | 690.0261 | 84253.1564 | 3446_f13c8c0a162;3535_64c816d67de
3528_8b65e7c0cfa | NA | 681.2041 | 55951.865 | 3457_dd4d75789cd;3533_3e01cdb8dca
3535_64c816d67de | NA | 667.0448 | 68574.5765 | 3446_f13c8c0a162;3539_b4812da0388
3533_3e01cdb8dca | NA | 582.7146 | 26337.9775 | 3457_246c0ff614d;3457_dd4d75789cd
3539_b4812da0388 | NA | 483.0562 | 37211.5549 | 3446_e070967a05e;3541_7265f4b6f50
3541_7265f4b6f50 | NA | 257.1682 | 22957.6341 | 3446_f4891677e7;3543_e0d68ca0d3b
3543_e0d68ca0d3b | NA | 51.3014 | 5478.7956 | 3446_f4891677e7;3544_d33f3befcd2
3544_d33f3befcd2 | NA | 46.4858 | 440.5038 | 3446_98f21802dc5

## GANTT
ID | MACHINE | START | DURATION | PROFIT | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
0 | 0 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 0 | 17 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1 | 14 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 2 | 76 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 2 | 29 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 0 | 63 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 2 | 25 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2 | 21 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0